## Actions

| # | Origin | Who | Action | Details | Need by |
| --- | --- | --- | --- | --- | --- |
|  | EIS opto-mechanical engineering meeting See EIS-meet-cons-9905agen & EIS-meet-cons-9905mins | 18-19 May 99 | NRL |  | dd/mm 1999 |
| 67 | -cons-9905n | MSSL:cjm | Comment on charge spreading | In EEV 42-10 devices. Effective resolution, mitigation options | 14/6 |
| 68 | “ | RAL:js | Advise John Seely on CF outgassing tests |  |  |
| 69 |  | NRL:js | Perform outgas tests | Report to consortium meeting | 14/6 |
| 70 |  | NRL:js + RAL:bk | Interpret results | Decide on further testing if necessary | 14/7 |
| 71 |  | NRL | Visible light analysis | e.g. Through filter pinholes | 1/7 |
| 72 |  | RAL | Venting analysis of structure | Suggest placement of vents and purge ports | 1/8 |
| 73 |  | BU | Update legs protocol memo |  | 14/6 |
| 74 |  |  | Revise optical design, reduce overall length by 10 cm …. | Define light-level regions Use Autocad (level compat. W/ BU) for drawing interchange Indicate origin of EIS coordinates at centre of aperture | 1/6 |
| 75 |  | NRL | use of 4200 lpmm grating |  |  |
| 76 |  | BU | Door design concept | Report of relative merits of SOHO-CDS and SOHO-LASCO door designs | 14/6 |
| 77 |  | NRL | Clamshell cost parameters | Investigate TRACE clamshell design, bring cost info to BU meeting Resposibility for provision of clamshell is TBD | 14/6 |
| 78 |  | NRL | Primary mirror mech design update | Forward mech interface details to Saad Mahmoud @ BU | 1/7 |
| 79 |  | NRL | Slit mech design update | To Saad | 1/7 |
| 80 |  | MSSL | Shutter mech design | To Saad | 1/7 |
| 81 |  | NRL | Grating mech design update | To Saad | 1/7 |
| 82 |  | NRL | Light Traps | Indicate approximate positions – to Saad | 14/6 |
| 83 |  | NRL | Baffles | Indicate approximate positions – to Saad | 1/7 |
| 84 |  | NRL/GSFC | Alignment Plan draft |  | 14/6 |
| 85 |  | MSSL | Flat Field lamp | Indicate ideal location | 1/6 |
| 86 |  | MSSL | Mech Design update | Base-mounted, size etc | 1/6 |
| 87 |  | MSSL/BU | Radiator size, placement |  | 14/6 |
| 88 |  | MSSL:cjm | Radiation | Comment on radiation - damage and spurious event Consider shielding requirement | 14/6 |
| 89 |  | RAL | Contamination Control plan | Report to cons meet | 14/6 |
| 90 |  | BU | Thermal control approach | Address heater position and power | 14/6 |