| Ops Exercises | Description | Duration | I&T Activity | Resources |  |  |  | Tool/Configuration |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | GSFC MOC | PSU MOC | GSFC I&T | KSC | S/C Bus | BAT | NFIs | HB |
| Pre-1 | Various Instrument and Spacecraft Bus Tests |  | General Testing |  |  | X |  | X |  | X | X |
| 1 and 2 | Standard Test Set: - Day-in-the-Life type activities - FOM Test with ToO Commanding - Other instrument/Science Activities - Normal Ops Activities | ~6 hours | Observatory Integrated Systems Test (IST) Dry Run | X |  | X |  | X |  | X |  |
| 3 | L&EO Dry Run to prepare for 1st L&EO Simulation | 12 hours |  | X |  | X |  |  |  |  | X |
| 4 and 6 | Solar Array Deployment Tests One of the few opportunities for FOT to see the realistic telemetry from this activities before launch | ~2 hours | Solar Array 1st Motion Deploy | X |  | X |  | X | X | X |  |
| 5 | Repeat OE#1 | ~6 hours | Observatory IST | X |  | X |  | X | X | X |  |
| 7 | NFI Door Deployments One of the few opportunities for FOT to see the realistic telemetry from these activities before launch | ~4 hours | NFI Deployment Tests | X |  | X |  | X | X | X |  |
| 8 | Repeat OE#4 | ~2 hours | Solar Array 1st Motion Deploy |  | X* |  | X | X | X | X |  |
| 9 | Repeat OE#1 | ~6 hours | Observatory IST |  | X* |  | X | X | X | X |  |

* Telemetry Monitoring Only

| L&EO Ops Sims | Description | Duration | I&T Activity | Personnel | Resource(s) |  |  |  | Tool/Configuration |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GSFC MOC | PSU MOC | GSFC I&T | KSC | S/C Bus | BAT | NFIs | HB |
| 1a_1 | Exercise 1st 2-3 days of L&EO Timeline/Script (compressed) - SSOH via TDRSS link post-separation - Monitor Solar Array Deployment (RTS execution) - Initial Acquisition with Malindi Subsystem Checkout - Clock Update - Ephemeris Update - CPU RAM Dumps - SSR Configuration and Dumps - EPS/AHI Configuration - Star Tracker Power On/Checkout - ACS Mode Transition (Inertial Pt.) | 2 days, 12 hours/day | Pre-BAT Delivery | - FOT - L&EO Dir. - Sim Eng. - MORL - SA Sys. Eng. | X |  | X |  | X |  |  |  |
| 1a_2 | Exercise ACS Slew Testing performed during L&EO (compressed) - ACS Mode Transition - Ephemeris Update - CPU RAM and SSR Dumps - Slew Tests - Torque Rod Compensation (TBD) | 1 day, 12 hours | Pre-BAT Delivery | - FOT - L&EO Dir. - Sim Eng. - MORL - SA Sys. Eng. - ACS Eng. | X |  | X |  | X |  |  |  |
| 1b_1 | L&EO NFI Activation Sequence (compressed) - S/C begins in Mission Mode and Inertial Point Mode - Box Power On - Telescope Configuration - Simulated door opening (as allowed) - Activation activities interleaved to simulate L&EO sequence - Power down due to SH - SH Recovery - Emergency Power Down | 3 days, 12 hours/day | Pre-BAT Delivery | - FOT - SA Sys. Eng. - UVOT Eng. - XRT Eng. | X |  | X |  | X |  | X |  |
| 1b_2 | L&EO FoM/ACS Interface Testing - FoM Checkout - Slew Tests with NFI boxes powered on (no telescopes) - Power on Telescopes - Run Open Door procs (no actual door opening) - Post-UVOT Door Open Slew Tests | 1 – 2 days, 12 hours/day | Pre-BAT Delivery | - FOT - SA Sys. Eng. - ACS Eng. - UVOT Eng. - XRT Eng. | X |  | X |  | X |  | X |  |
| 1b_3 | L&EO Timeline/Script Sequence (compressed) - NFI Box Activation Activities - BAT Activation Activities (through 1 – 2(?) DM Blocks) - SADA Characterization - Antenna Switch Test (?) Nominal Slews requiring SADA motion | 3 transitions, ~12 hours per transition | Thermal Vacuum (TVAC) Transitions | - FOT - SA Sys. Eng. - ACS Eng. - NFI Engs. - BAT Eng. | X |  | X |  | X | X | X |  |
| 1c | Final Full L&EO Simulation before Launch Site - Repeat Sim 1a_1 - Include minimum Instrument Electronic Box Power Up (XRT, UVOT, BAT) | 2 days, 12 hours/day | L&EO Rehearsal | - All engineers supporting L&EO |  | X | X |  | X | X | X |  |
| 1d | Final Full L&EO Simulation (Repeat Sim 1a_1) | 2 days, 12 hours/day | Observatory ETE | - All engineers supporting L&EO |  | X |  | X | X | X? | X? |  |

| Post-L&EO Ops Sims | Description | Duration | I&T Activity | Personnel | Resource(s) |  |  | Tool/Configuration |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GSFC MOC | PSU MOC | GSFC I&T | S/C Bus | BAT | NFIs | HB |
| 2a | Enhanced “Day-in-the-Life” Simulation - Instrument Power On (SH Recovery) - Stimulate Instruments, as available - FOT Routine Operations Activities - ATS upload - CPU RAM/SSR Playback - Clock & Ephem Updates - Science Plan/Replan/Timeline Delivery - Nominal Instrument Commanding - 72-hour “hand off”/weekend ops with PSU automation (?) - 73-hour time-out with SH Recovery - BAT FoV/Source Test (BAT ETE) | 2 days, 24 hours/day | Observatory Operations Test (formerly, Observatory Science End-to-End Test) | - FOT - SA Sys. Eng. - Inst. Engs. - SDC(?) – depends on PSU MOC | X? | X? | X | X | X | X |  |
| 2b | “Day-in-the-Life” Test - FOT Normal Operations Activities (see 2a) - Routine Instrument Commanding | ~12 hours | Thermal Balance | - FOT - All Subsystem Engs. - Inst. Engs. | X |  | X | X | X | X |  |
| 2c | Paper Simulation of Daily Operations (using the PSS or Recorded Data) - Coordinate Operational Product Deliveries - Science Planning/Replanning - FOT/SOT Nominal Activities - File Transfers - Other Activities as needed | 2 days, 8 hours/day |  | - FOT - Inst. Engs. - SDC - Data Centers |  | X |  |  |  |  |  |

| Contingency Sims | Description | Duration | I&T Activity | Personnel | Resources |  |  |  | Tool/Configuration |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GSFC MOC | PSU MOC | GSFC I&T | KSC | S/C Bus | BAT | NFI | HB |
| 3a_1 | Special Operations Simulation - Observatory configured for normal operations with NFIs online - CPU RAM/SSR Playback - RTS Load/Dump - NFI FSW and Table Uploads/Dumps - SOH Verification (S/C Bus, NFIs) | 3 days, ~8 – 10 hours/day | SCIF #4A | - FOT - S/C Bus Sys. Eng. Support - NFI Engs. |  | X | X |  | X |  | X |  |
| 3a_2 | Special Operations Simulation - Observatory configured for normal operations with instruments online - CPU RAM/SSR Playback - ATS and RTS Loads/Dumps - S/C Bus and BAT FSW and Tables Uploads/Dumps - S/C Bus and Instrument Real-Time commanding - TDRSS Burst Messages - SOH (Observatory) | 1.5 days, ~12 hours/day | SCIF #4B | - FOT - S/C Bus Engs. - Inst. Engs. |  | X | X |  | X | X | X |  |
| 3a_3 | Special Operations Simulation - HB configured for normal operations with instrument ETUs online - CPU RAM/SSR Playbacks - S/C Bus and Instrument FSW and Table Loads/Dumps - S/C Bus and Instrument Real-Time commanding - TDRSS Burst Messages - SOH (Observatory) | 2.5 days, ~12 hours/day | SCIF #4C | - FOT - SA Sys. Eng. |  | X |  |  |  |  |  | X |
| 3b | ## L&EO Contingency Sim – 1st Anomaly Simulation - Details developed at later date by - Simulation Engineer - Observatory Systems Engineer - Observatory I&T Manager - MOT participants will not be briefed on details for training purposes | ~12 hours |  | - FOT - All S/C Bus Engs. supporting L&EO - Inst. Engs. |  | X | X |  |  |  |  | X |
| 3c | L&EO Contingency Sim 2nd Anomaly Simulation (Repeat Sim 3b with different anomalies) | 1 day, ~12 hours | L&EO Contingency Rehearsal | - FOT - All S/C Bus Engs. supporting L&EO - Inst. Engs. |  | X | X |  | X | X | X |  |

| Ops Readiness Test | Description | Duration | Resources |  |  |  |  | Tool |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | PSU MOC | KSC | Malindi | USN | TDRSS | Observatory | PSS | Tape |
| 1 and 2 | Nominal Pass Ops - Voice Communications - Pre-pass ground system configuration and connection w/ station - Real-Time Commanding Activities - No-ops - Clock Update - ATS Load - Post-pass activities - Data Transfer | ~4-8 hours | X |  | X |  |  |  | X |  |
| 3 and 4 | Contingency Pass Ops - Activities from ORT #1 - Blind Acquisition - Negative Acquisition | ~4-8 hours | X |  | X |  |  |  | X |  |
| 5 and 6 | Nominal Pass Ops - Same as ORT #1 | ~4-8 hours | X |  |  | X |  |  |  | X |
| 7 and 8 | Contingency Pass Ops - Same as ORT #3 | ~4-8 hours | X |  |  | X |  |  |  | X |
| 9 (TBD) | Nominal Pass Ops - Voice Communications - Pre-pass ground system configuration and connection w/ station - Real-Time Commanding Activities - No-ops - Post-pass clean-up | ~4-8 hours | X | X |  |  | X | X |  |  |